## Risk Register
SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register
SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register | SeaNergy risk register
SIH 2026 ¦ likelihood and impact scored 1-5 ¦ named primary and backup ownership
ID | Risk | Category | Likelihood | Impact | Score | Level | Mitigation | Owner / backup | Trigger / fallback / status
R-01 | Peripheral bus cannot sustain required sample rate | Firmware | 3 | 5 | 15 | High | Benchmark DMA path; reduce copies; reserve deterministic buffer | Pulkit / Harshada | Trigger: missed buffer deadline. Fallback: known safe sample profile. Active
R-02 | Transducer resonance shifts in mounted or wet condition | Acoustics | 4 | 4 | 16 | High | Measure impedance and sweep after mounting; keep solver down-band margin | Pulkit / Harshada | Trigger: peak shifts beyond calibration band. Fallback: characterized safe frequency. Active
R-03 | Venue restricts water, mains or open bench activity | Demo | 3 | 5 | 15 | High | Pre-clear setup; sealed tray; battery operation; dry demonstration ready | Pulkit / Ananya | Trigger: venue restriction. Fallback: dry bench plus synchronized trace replay. Active
R-04 | Critical component or board fails | Hardware | 3 | 5 | 15 | High | Carry programmed spare board, sensors, fuse, cables and known-good image | Pulkit / Harshada | Trigger: no boot/output after one reset. Fallback: spare board and recorded trace. Active
R-05 | Offline firmware update bricks controller | Firmware | 2 | 5 | 10 | Medium | Signed known-good binary; recovery cable; protected release image | Pulkit / Harshada | Trigger: boot loop. Fallback: ROM recovery and spare board. Active
R-06 | Water and mains create an electrical safety event | Safety | 2 | 5 | 10 | Medium | Battery-first setup; RCD/isolation; drip tray; physical separation; safety owner | Ananya / Harshada | Trigger: leak, wet connector or protection trip. Fallback: de-energize and dry demo. Active
R-07 | Ambient acoustic noise masks received signal | Acoustics | 4 | 4 | 16 | High | Coded waveforms, matched filtering, close-range target and noise capture | Pulkit / Harshada | Trigger: SNR below demo threshold. Fallback: electrical output plus recorded water trace. Active
R-08 | Six-minute slot overruns | Presentation | 3 | 4 | 12 | Medium | Timed script, fixed transitions, 90-second close and visible timer | Aarushi / Pulkit | Trigger: 4:30 without market section. Fallback: jump to headline evidence and ask. Active
R-09 | Panel lacks acoustic specialization | Presentation | 3 | 3 | 9 | Medium | Lead with user outcome, animation and three plain-language numbers | Aarushi / Pulkit | Trigger: terminology questions dominate. Fallback: analogy-first explanation. Active
R-10 | Primary subsystem owner is absent | Team | 2 | 5 | 10 | Medium | Assign backup for every subsystem; print runbook; cross-rehearse | Pulkit / Ananya | Trigger: absence or travel delay. Fallback: backup owner and reduced live scope. Active
R-11 | Patent-sensitive detail is disclosed before filing | IP | 2 | 5 | 10 | Medium | Disclosure hold, controlled review links and release approval | Aarushi / Ananya | Trigger: public upload request. Fallback: redacted architecture until receipt. Active
R-12 | Imported component price or delivery changes | Supply | 4 | 3 | 12 | Medium | Dual-source connectors and power parts; keep INR contingency and substitutes | Harshada / Pulkit | Trigger: lead time exceeds integration gate. Fallback: bench-equivalent part. Active
R-13 | Mobile or wireless link drops during demonstration | Software | 3 | 3 | 9 | Medium | Local USB path, offline build, cached traces and fixed device pair | Prakhar / Jaspreet | Trigger: no telemetry for 10 seconds. Fallback: local dashboard. Active
R-14 | Calibration settings are overwritten | QA | 2 | 4 | 8 | Medium | Versioned calibration file, checksum, read-only release copy | Jaspreet / Pulkit | Trigger: checksum mismatch. Fallback: restore signed calibration pack. Active
R-15 | Final integration compresses rehearsal time | Schedule | 3 | 4 | 12 | Medium | Freeze interfaces, protect rehearsal gates and defer noncritical polish | Pulkit / Ananya | Trigger: integrated flow incomplete by 5 Oct. Fallback: stable reduced scope. Active

## Heat Map
Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map
Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map | Risk heat map
Count of active risks by likelihood and impact
Likelihood | 1 | 2 | 3 | 4 | 5 | Row total
5 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 1 | 2 | 0 | 3
3 | 0 | 0 | 2 | 2 | 3 | 7
2 | 0 | 0 | 0 | 1 | 4 | 5
1 | 0 | 0 | 0 | 0 | 0 | 0
Column total | 0 | 0 | 3 | 5 | 7 | 15
Level | Count | Definition
High | 5 | Score 15-25; fallback mandatory
Medium | 10 | Score 8-14; mitigation and trigger tracked
Low | 0 | Score 1-7; monitor

## Scoring Guide
Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide
Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide | Scoring and ownership guide
Every risk has a named primary owner and operational backup
Score | Likelihood | Impact | Response
1 | Rare | Negligible; no demo effect | Monitor
2 | Unlikely | Minor degradation | Owner action
3 | Possible | Visible degradation or rework | Mitigate and rehearse
4 | Likely | Major subsystem or schedule effect | Fallback prepared
5 | Almost certain | Safety, filing, submission or demo failure | Immediate control and fallback
High-risk rule | Required fields | Review point | Closure evidence
Score >= 15 | Named owner, trigger, mitigation, fallback | Each integration/rehearsal gate | Recorded drill or risk reduction